## Sheet1
DETAILS OF PROJECTS
Name of Supporting Person :SHABEER ASHKAR | Name :SUJITH
Area of Supports:ALL DIVISION | TECHNICAL SUPPORT ENGINEER
Requirements | Requested Date | Projected Start Date | Projected end date | Actual Starting Date | Change Request Date and Comment* | Revised Expected End date | Date of Completion | Delayed days Number of Days/On Time | Reason for Delay | Current Status
CCTV CONFIG IN FMCG BRANCHES | 2022-08-30 | AUGUST |  | 2022-08-01 |  |  |  |  | INTERNET AND CABLING ISSUES | WORK NOT COMPLETED
ACCESSCONTROL INSTALLATION IN HO | 2022-09-10 | SEPTEMBER |  | 2022-09-20 |  |  |  |  | SERVER MIGRATION | ACCESSPOINTS WORKING OK.
FORTINET VPN CONFIGURATION IN FMCG BRANCHES | 2022-09-10 | SEPTEMBER |  | 2022-09-11 |  |  |  |  | WINDOWS UPDATION | 2 BRACHES PENDING
FORTINET VPN CONFIGURATION IN HO | 2022-09-10 | SEPTEMBER |  | 2022-09-11 |  |  |  |  | PENDING | WORK GOING ON
TELEPHONE CONFIGURATION | 2022-08-24 | AUGUST |  | 2022-08-26 |  |  |  |  | CABLE ISSUES | PENDING
Instruction:-
* Right-click the cell and then click Insert Comment* (column H)
Note on L6: Author: Started Branches Calicut Bathery Thalamala Malappuram